## Slide 1: Sample Risk Mitigation Plan
One East Coast healthcare system undergoing a large-scale IT system implementation to replace acute, ambulatory, and revenue cycle systems developed risk mitigation plans that addressed clinical, revenue cycle, and operational risks.
Integrated work groups of clinical operations and revenue cycle staff were important factors in identifying and addressing how clinical changes would impact billing. Also critical to success was representation and participation from all three hospitals in the work groups to promote consistent workflows, processes, and procedures across locations.
See related article: The Art of Execution: Identifying and Mitigating Risks in Healthcare Provider Organizations

## Slide 2: ARCR Risk
Risk: HIM Staff Productivity | Owner: XXX | Status: In Progress
Increase in discharge not billed (DNB) and inability to maintain; prevent negative impact on DNB; spikes in accounts receivable (A/R) Learning curve impact on health information management (HIM) staff ability to maintain productivity levels (Coding and clinical documentation improvement [CDI]) |  | 
Next Steps: HIM Leadership is working on increasing the amount of contract coding staff (create bench) to provide coverage as needed. Challenge on vendor side for recruitment, but is being actively addressed. Mitigate training of contract staff by providing web-based training option. Concern for new and additional contract staff added after go-live that will need access to electronic health record; training requirements before access. Ensure that the physician training meets HIM coding needs, as well as monitoring any technical issues that arise from the 3M 360 software/electronic health record integration. |  | 
Status Update: Operations is handling next steps. There will be an update week of 2/19 regarding the level of bench staff trained and for go-live and is being actively monitored. |  | 

## Slide 3: ARCR Risk
Risk: Patient Access / Registration Training | Owner: XX | Status: In Progress
Training outcomes did not match future state workflow needs. Workflows trained did not include additional built items that were only recently finalized. For example Cardiac Cath, Surgical Services, TEE/Cardioversions. Workflows that are still open such as advance beneficiary notices of noncoverage (ABNs) for hospital outpatient departments (HODs) and infusion blood type and crossmatch will need to be trained once finalized |  | 
Next Steps: Weekly meeting is established between project team and operations to ensure training outcomes are positive. Training format has been changed to a more interactive experience. Super users will be brought back for training on 2/22 or 2/23 to review all registration workflows after the workflows are finalized. Managers on campus are establishing registration training worklabs to perform one-on-one training and ensuring a minimum of 50 scenarios are performed in the playground Managers have increased the scenarios to mirror current operations to ensure workflow understanding Training on ABNs for HODs and Infusion Blood Type and Cross will be established once the workflow is finalized Readiness team will pull together all tip sheets to distribute to the registration teams at go-live |  | 
Asks: No asks at this time Status Update: Move to Closed, Operations is Well Prepared. |  | 
Source: Virtua and The Chartis Group. Used with permission.