## Event Planning
Event
Event Date | 2024-10-01
Timing | Responsible Committee | Category | Action Item | Description/notes | Deadline (Weeks From event) |  | Due Date | Individual Owner by name
1 - Pre-Event | Event Committee | Education/Sessions Development | Agenda/Speaker/Sponsorship Development | Begin planning process for event | 12 | 84 | 2024-07-09
1 - Pre-Event | President-Elect | Venue Management | Identify education event location | Research, identify, and procure a location for the event | 12 | 84 | 2024-07-09
1 - Pre-Event | Event Committee/Administrator | Education/Sessions Development | Create request for event set-up in Cvent with Association | Work with Association's One HFMA Team to create event within Cvent, including addition to calendar and save the date email | 12 | 84 | 2024-07-09
1 - Pre-Event | Event Committee | Education/Sessions Development | Submit Event Date Reservation Form to the President-Elect | Per Policy A03, Facilities Reservation Request | 12 | 84 | 2024-07-09
1 - Pre-Event | Board Liaison | Education/Sessions Development | Present agenda for Board approval |  | 8 | 56 | 2024-08-06
1 - Pre-Event | Event Committee | Cvent Prep | Complete agenda | Provide final agenda to Association for Cvent update | 8 | 56 | 2024-08-06
1 - Pre-Event | Event Committee/Administrator | Education/Sessions Development | CPE calculation | Submit agenda for CPE calculation to NJCPA Liaison | 8 | 56 | 2024-08-06
1 - Pre-Event | Event Committee/Program Chair | Education/Sessions Development | ACHE Credit Calculation | Different from CPE calculation | 8 | 56 | 2024-08-06
1 - Pre-Event | Event Committee | Cvent Prep | Speaker bios & headshots | Provide to Association for Cvent update | 8 | 56 | 2024-08-06
1 - Pre-Event | President-Elect | Venue Management | Happy Hour Location Details (if applicable) |  | 8 | 56 | 2024-08-06
1 - Pre-Event | Event Committee | Cvent Prep | Solicit sponsors, if applicable. Inform Cvent team as needed |  | 8 | 56 | 2024-08-06
1 - Pre-Event | Administrator | Cvent Prep | Obtain speaker registration code from the Association |  | 8 | 56 | 2024-08-06
1 - Pre-Event | Administrator | Cvent Prep | Obtain sponsor registration code from the Association |  | 8 | 56 | 2024-08-06
1 - Pre-Event | Event Committee | Marketing Materials | Create Flyer for email, social media |  | 6 | 42 | 2024-08-20
1 - Pre-Event | Event Committee | Marketing Materials | Schedule weekly highlights and promotions with Administrator and Social Media Chair |  | 6 | 42 | 2024-08-20
1 - Pre-Event | Event Committee | Speaker Management | Speaker Huddle | Consider having a 'speaker huddle' especially for panels to review general logistics/overview of event/timing of everything with speakers | 2 | 14 | 2024-09-17
1 - Pre-Event | President-Elect | Venue Management | Head Count Update and Dietary Restrictions | Send co-chairs any dietary restrictions received in registrations. Co-chair to send venue request for dietary restrictions. | 1 | 7 | 2024-09-24
1 - Pre-Event | President-Elect | Venue Management | Confirm contract timing has food breaks aligned with actual agenda |  | 1 | 7 | 2024-09-24
1 - Pre-Event | President-Elect | Venue Management | Confirm number of tables/room set up/placement of exhibitors |  | 1 | 7 | 2024-09-24
1 - Pre-Event | Event Committee | Sponsorship | Obtain current listing of sponsors for inclusion in rotating slides |  | 1 | 7 | 2024-09-24
1 - Pre-Event | Administrator | Badges | Ensure adequate supply of badges |  | 1 | 7 | 2024-09-24
1 - Pre-Event | Event Committee | Education/Sessions Development | Speaker introductions | Assign speaker introductions to committee member | 1 | 7 | 2024-09-24
1 - Pre-Event | Event Committee | Speaker Management | Load presentations on thumb drive | Includes all speaker presentations, introduction slides | 1 | 7 | 2024-09-24
1 - Pre-Event | Administrator | Speaker Management | Load presentations on web page and provide link to attendees | Includes all speaker presentations, introduction slides | 1 | 7 | 2024-09-24
1 - Pre-Event | Administrator | Speaker Management | Confirmed Speaker Registration | Confirm with cvent committee that all speakers are registered | 1 | 7 | 2024-09-24
1 - Pre-Event | Event Committee | Speaker Management | Speaker Logistics | Coordinate with each speaker to arrive 1 hour before their presentation, note a meeting spot for co-chair to find them when they arrive at venue, share contact/cell info in advance | 1 | 7 | 2024-09-24
1 - Pre-Event | Event Committee | Venue Management | Review technology and AV needs – laptop, projectors, clickers, two screens vs. one screen projection. |  | 1 | 7 | 2024-09-24
2 - Day Of Event | Administrator | Badges | Name Badges and Name Badge Holder |  | 0 | 0 | Day of or Day Before Event
2 - Day Of Event | Administrator | Sign In Sheets | Sign-in Sheets | Check in and CPE sign in (am & pm) | 0 | 0 | Day of or Day Before Event
2 - Day Of Event | Event Committee | Technology/AV | Chapter laptop and Projector(s) | Run software updates (as needed) before day of event, load slides to share drive for easy access the day of. Confirm passwords as needed | 0 | 0 | Day of or Day Before Event
2 - Day Of Event | Event Committee | Day of Volunteer Roles | Registration Desk |  | 0 | 0 | Day of or Day Before Event
2 - Day Of Event | Event Committee | Day of Volunteer Roles | Mic Runner (2) |  | 0 | 0 | Day of or Day Before Event
3 - Post-Event | Event Committee | Communications | Submit write-up of event to Communications Committee | For publishing in the Garden State Focus | -1 | -7 | 2024-10-08
3 - Post-Event | Board Liaison | Financial Close process | Reimburse speakers as necessary |  | -1 | -7 | 2024-10-08
3 - Post-Event | Event Committee | Speaker Management | Email speaker thanking them for speaking |  | -3 | -21 | 2024-10-22
3 - Post-Event | Administrator | Communications | Distribute event surveys within 24 hours of event, reminder blasts distributed a week later |  | -1 | -7 | 2024-10-08
3 - Post-Event | Event Committee/Adminsitrator | Financial Close Process | Send happy hour expenses/reimbursement to event co-chairs and treasurer |  | -3 | -21 | 2024-10-22
3 - Post-Event | Treasurer | Financial Close Process | Complete a final P&L |  | -4 | -28 | 2024-10-29
Formulas:
Due Date = IF([Deadline (Weeks From event)]=0,"Day of or Day Before Event",B2-G5)